## Best Practices
Best Practices for Global Template & Rollout Programs
The aspects mentioned in the following table should be considered as a non-exhaustive checklist for your global template initiative. You can add additional items or use the list to assess which level of excellence you have achieved currently in the different sections.
Topic | Best Practice Aspects for Topic | Rating of current Level achieved
|  | Not practiced | Basic Practice | Common Practice | Advanced Practice | Best Practice
Business Processes
Costs and benefits of a process standardization and harmonization are described and evaluated in a busines case
A business process master list / business process map has been set up
All processes are described in sufficient detail (at least 3 levels, e.g. Main Process, Process, Process Step) in an appropriate form (e.g. process description as text + user requirements + process flowchart)
All processes include a description who is involved in the execution of this process (match of executing organizational units per process step)
All processes include a description which IT systems are involved in the execution of this process
Rules are in place that define if a process is a variant of another process or if a process is actually a new process
Rules are in place that define if a template process has to be used or if a new process can be requested
It is the objective of a template process to use it for as many organizations as possible
An appropriate tool is used to describe and document a process (e.g. ARIS, VISIO)
Processes used by more than one organization or all organizations are classified as global processes and are part of the global template
Processes used only by one organization are classified as local processes
All legal requirements for the involved countries are identified and clearly described
All regulatory requirements for the involved countries / industries are identified and clearly described
Monitoring functionalities are available to prevent and detect process isssues
Master Data
All data are defined and described in a data handbook
Data quality criteria needed to support the program and project objectives are defined
Data quality is regularly measured with appropriate KPI's.
Data standards are defined for all data attributes that need to be harmonized
Costs and benefits of a data standardization and harmonization are described and evaluated in a busines case
For each data attribute is is defined who uses this attribute and who will be impacted by a change
For each data entity / attribute is is defined where it is stored and which system is leading for entity / attribute maintenance and distribution
For each attribute of a data entity it is defined if this attribute has global or local relevance
Attributes defined as global are maintained centrally
Attributes defined as local are maintained locally
All legal requirements for the involved countries are identified and clearly described
All regulatory requirements for the involved countries are identified and clearly described
Centrally maintained data attributes are automatically distributed to all systems where needed
Data maintenance procedures are supported by automated workflows
Organization
A program management team has been defined with a description of tasks and responsibilities for each team member
A program manager has been nominated
The program management team includes major stakeholders from business and IT
For each rollout project a project management team has been defined with a description of tasks and responsibilities for each team member
A rollout project manager has been nominated
For all business processes process owners and stewards have been defined
For all data enties / attributes of an entity data owners and stewards have been defined
For each role in the program / project a description of tasks, responsibilities and required skills is available
A change advisory board CAB has been established that is resonsible for the approval of changes
A QA has been established for program and projects
Teams for the processes are defined as appropriate (e.g. E2E process teams or functional teams)
Governance
Process owners / process stewards are defined
Data owners / data stewards are defined
It is clearly defined what a change is
A procedure how to deal with changes is in place
Changes are classified concerning risk, impact and implementation efforts
A change advisory board CAB has been established that is resonsible for the approval of changes
Clear rules are in place when an organization has to use an existing process, when a variant will be created or when a new process will be created
For elements that are usually independent of an organization no organizational dependency will be created without a need (e.g. do not copy document types for each organization)
Organizational and technical measures ensure that configurations of a project running in parallel to another project do not interfere
Organizational and technical measures ensure that changes made by one project do not interfere or invalidate tests of another project
Changes are collected and set productive on the basis of a planned schedule (Release Management)
Program + project management uses a generally accepted standard (e.g. PMI, PRINCE2) or inhouse standard
Controls are in place to manage program / project / operational risks
Organizational Change Management
A global change manager has been nominated
Change managers for each rollout have been nominated
All stakeholders have been identified and their expectations for the program / project have been captured
Organization understands what a template is and what the impacts of a template are, e.g. use of common standards
Impacts of changes on current procedures are identified and described
All stakeholders are aware of the umcoming changes and have committed to the implementation
A regular communication about the program / projects has been established
Changes are addressed in the trainings and are included in training documents
Trainings are scheduled early to ensure that people supporting the program / projects have the required skills before activities start (e.g. language trainings)
A procedure how to deal with resistance to change is in place
Stakeholders provide sufficient and qualified people for the program / projects
Testing
Test cases are defined
Test data for the test cases are defined
Test data can easily be generated (e.g. by TDMS) and are reusable
Test types are defined for different tests in different project phases (e.g. Unit Tests, Integration Tests, User Acceptance Tests)
People assigned for testings have been trained how to test
Test systems have been set up
A test concept is available
The execution of tests is supported by appropriate tools, e.g. Solution Manager
Test plans are described
For each test it is defined in which system the test is done, which data are used, who is doing the test and which test result is expected
Controls are in place to ensure that sensitive test data can only be accessed / viewed by authorized staff or is anonymized.
It is clearly described for which tests migrated data are prerequisite (e.g. User Acceptance Tests)
Tests can be executed automatically (e.g. needed for Regression Tests)
Testing can ensure that all user requirements have been tested (using Traceability Matrix)
Testing encompasses tests of single functionalities (e.g. Unit Tests) as well as tests of E2E process scenarios (e.g. Integration Tests)
Information about impacts of changes is available for regression tests
Tests are defined for positive tests (User Acceptance Test) and negative tests (Regression Test)
Training
A training concept is available
A training coordinator has been nominated
Trainings are scheduled early to ensure that people supporting the program / projects have the required skills before activities start (e.g. language trainings)
It is ensured that people have completed their trainings before getting access to the productive system
Success of training has been measured or mechanisms are in place for people to check their score
Training is continued as needed also after Go Live
Training documents are available in the language the end users can understand
Plannings include the efforts for creating and translating training documents
Trainings are available as classroom trainings or online trainings for self-study
Training systems are available (e.g. Sandbox)
Trainings use representative data (no Dummy Data)
Validation (Pharma-specific)
A validation plan has been created
User requirements fulfill the following criteria: understandable, necessary, modifiable, nonredundant, terse, testable, traceable, within scope
The quality of the user requirements is checked by QA
GMP-critical requirements, processes, data, authorizations and transactions are identified
A traceability matrix for tracking user requirements, their implementation and test has been set up
The validation phases DQ, IQ, OQ, PQ ae aligned with the project plan
Validation has issued SOP's for all relevant areas of the program / projects
A global responsible for validation has been nominated
For each rollout project a local responsible for validation has been nominated
Validation controls are in place
Data Migration
A global data migration coordinator has been nominated
Data migration coordinators for each rollout have been nominated
Awareness workshop for data migration has been done with the stakeholders
Data cleansing activities have been triggered in time and can be completed before rollout starts
Master data to be migrated are described in detail
Transactional data to be migrated are described in detail
A field mapping for all fields exists (Source System --> Target System)
Conversion rules are described in detail
Data migration tools have been selected (e.g. LSMW)
Templates for data migration objects (MOL's) are defined
Data migration test systems have been set up
Data migration test systems are supplied with configuration changes from DEV to ensure that system configurations are consistend with DEV - QA - PROD stream
Efforts for supporting data migrations by functional teams are included in the project planning
All data source systems are identified
All data owners for data to be migrated are identified
Test cases for data migration tools are defined
Correctness of migrated data must be approved by data owners
Procedures for downloading / uploading data has been defined
Controls are in place to ensure that sensitive data can only be accessed / viewed by authorized staff or is anonymized.
Data migration can provide test data for specific test types, e.g. User Acceptance Tests
IT Applications
For all IT applications at least the following system types have been set up: Development DEV, Quality Assurance QA, Production PROD
The system landscape with all applications is described
A description exists that maps business processes and process steps onto applications supporting the process and process step execution
A list of all interfaces is available. Description includes at least direction of interface (Inbound, Outbound), type of business content transferred and timing of transfer (sysnchronous, asynchronous)
A list of all reports is available
Elements that are used for more than one project are assigned to program responsibles, e.g. developments, client-independent elements
Elements that are used for one project only are assigned to project responsibles, e.g. client-dependent elements
Impacts of configuration changes on processes and organizations can be simulated
IT Infrastructure + SAP Basis
IT Infrastructure uses a process model (e.g. ITIL) as a reference
A support organization following the standards of a CCoE has been set up
Monitoring functionalities are available to prevent and detect malfunctions
Support
A support organization following the standards of a CCoE has been set up
A ticket system is used to track all kind of issues from projects and operations
Each organization has nominated key users
After Go Live a phase has been planned with intensified on-site support
Authorizations
Authorization concept is in place
Master roles are defined
Procedure how to create derived roles from master roles is described
Critical authorizations are identified
A segregation-of-duties matrix SOD has been set up
Authorization concept fulfills SOD requirements
Authorizations ensure that sensitive data can only be accessed / viewed by authorized staff or is anonymized.
Authorization concept supports roles in a Shared Service Center
Tests for authorizations are defined
Process of assigning / revoking authorizations is implemented efficiently (e.g. as automated workflow)
Changes of master roles are subject to change request procedure
Authorizations are documented from a business point of view so that business can understand what to request or approve
Quality Assurance
Quality assurance is independent of the program / project management
Quality assurance checks formal quality, content quality and alignment of program / project with Best Practices
Quality checks are part of the program / project planning and are part of the project plan or can be initiated as needed
Strategy
Business and IT strategy are described and have been broken down into program requirements
A business case for the program and the projects is available
The program has been discussed with the stakeholders to ensure that it supports the strategies of business and IT
Appropriate KPI's are in place to measure if benefits have been achieved
Documentation
Common tools for documentation have been defined
All teams document their work in the same form using the same templates and documentation tools
It must be planned and scheduled when changes of documents become effective.
Documents relevant for more than one organization are maintained centrally and are referenced.
Documents relevant for more than one organization are part of the global template
Documents relevant for only one organization are part of the rollout project
A process exists that describes the steps for transforming a local document into a global document
Layout and content of documents must be kept seperate. It must be possible to change a layout without having to create a new document
Changes of document templates are subject to change requests
Clear rules have been defined when a new version of a document must be created
Clear rules have been defined if a document shall be copied or is referenced
Clear rules have been defined which documents must be approved. Such documents include at least responsibilities for Creation, Review, Approval
Tools
Tools for documentation must support versioning of documents
Tools for documentation must support the creation of flowchart representations
Approval procedures are supported by automated workflows
Tools support electronic signatures
Tools support a solution monitoring concerning detecion and prevention of issues and malfunctions
Tools support the automated execution of tests
Copyright consulting4bit June 2012