## Template Scenario Evaluation
Global Template Scenario Evaluation Scheme
Objectives of the Global Template Project | Weight | Option 1 | Option 2 | Option 3 | Score Option 1 | Score Option 2 | Score Option 3
Business Globalization | 7 | 2 | 3 | 4 | 14 | 21 | 28
Improvement of Business Processes | 6 | 1 | 3 | 4 | 6 | 18 | 24
Business Flexibility & Agility | 5 | 2 | 3 | 4 | 10 | 15 | 20
Business Requirements | 7 | 3 | 3 | 3 | 21 | 21 | 21
Legal & Compliance Requirements | 8 | 3 | 4 | 4 | 24 | 32 | 32
Standardization & Harmonization of Business Processes | 3 | 2 | 4 | 4 | 6 | 12 | 12
Standardization & Harmonization of Master Data | 4 | 2 | 3 | 4 | 8 | 12 | 16
Shared Services | 5 | 4 | 3 | 2 | 20 | 15 | 10
Modernization of Technology | 6 | 2 | 4 | 4 | 12 | 24 | 24
Documentation | 8 | 3 | 4 | 4 | 24 | 32 | 32
Implementation Costs | 6 | 5 | 3 | 2 | 30 | 18 | 12
Total Score |  |  |  |  | 175 | 220 | 231
Note on B2: Priority of this objective Set a value from 0 to 10
Note on C2: Weight indicates how well the option supports the achievement of the objective

## Risk Assessment
Exercise for Risk Assessment
Instruction: Please estimate impacts and probability for the ten exemplary typical risks of a global template project.
Assgin values between 0 (=no impacts, probability is zero) and 10 (very high impacts, very high probability)
Value Name | X (Impact) | Y (Probability)
Very Low | 0-2 | 0-2
Low | 2-4 | 2-4
Medium | 4-6 | 4-6
High | 6-9 | 6-9
Very High | 8-10 | 8-10
Risk Name | X Value | Y Value
Lack of Resources | 5 | 6
Lack of Skills | 5 | 7
Unclear Objectives | 7 | 6
Lack of Committment | 7 | 5
Unclear Requirements | 3 | 9
Requirements not covered | 6 | 9
Bad Data Quality | 7 | 2
Technology unstable | 8 | 3
Resistance to Change | 3 | 5
Frequent Change Requests | 9 | 8

## Rollout Sequence Planner
Template Rollout Sequence Planning
Project Name | Offset | Preparation | Blueprint | Realization | Final Preparation | Go Live & Support | Total Duration
Project 1 | 0 | 1 | 3 | 3 | 1 | 1 | 9
Project 2 | 0 | 1 | 3 | 3 | 1 | 1 | 9
Project 3 | 3 | 0.5 | 1 | 1 | 1 | 0.5 | 4
Project 4 | 12 | 0.5 | 1 | 1 | 1 | 0.5 | 4
Project 5 | 6 | 0.5 | 2 | 2 | 1 | 0.5 | 6
Project 6 | 6 | 0.5 | 2 | 2 | 1 | 0.5 | 6
Project 7 | 9 | 1 | 3 | 3 | 1 | 1 | 9
Project 8 | 9 | 1 | 3 | 3 | 1 | 1 | 9
Project 9 | 9 | 0.5 | 2 | 2 | 1 | 0.5 | 6
Project 10 | 12 | 0.5 | 2 | 2 | 1 | 0.5 | 6
Project 11 | 9 | 0.5 | 2 | 2 | 1 | 0.5 | 6
Project 12 | 12 | 0.5 | 2 | 2 | 1 | 0.5 | 6
Project 13 | 9 | 0.5 | 1 | 1 | 1 | 0.5 | 4
Project 14 | 9 | 0.5 | 1 | 1 | 1 | 0.5 | 4
Project 15 | 6 | 0.5 | 2 | 2 | 1 | 0.5 | 6
Note on B3: Starts in n Month relative to Start of First Rollout
Note on C3: Duration in Month
Note on D3: Duration in Month
Note on E3: Duration in Month
Note on F3: Duration in Month
Note on G3: Duration in Month
Note on H3: Duration in Month